## Iteration three
Must
| M (new) 2PP | M (was S) 1PP | M (new) 6PP | M (was W) 2PP
| As an user I want to see the state of an event | As an user I want to be able to tell that an event is over | As a user I want to access my account from a different location | As an observer I would like to see where every incident is located in the interactive map
Define database 1PP
Write PHP or other access mechanism 2PP
Java interface to server 3PP
Should
| S (new) 4PP | S (new) 6PP
| As an user I want to report an event in free text format | As a user I want to see events created by other users potentially at a different loction [assuming DataBase exists]
Extend database 1PP
Extend PHP or other access mechanism 2PP
Java interface to server 3PP
| New S 2PP | New S 4PP | S 2PP
| As an user, I want to delete my account | As an user, I want to add information to an event | As an user I want to see the alerts on the top of the list
Could
| C 2PP | C (was S) 6PP | C 3PP
| As a user I want to vote for the urgency of an event and validate this property | As a helper I only want to see events where I can help (assumption: list of events exists, including locations) | As a journalist I want to provide information that helps to validate the severity of a given event
Task: categorizing of events 4PP
Task: showing selection 4PP
Would
| W (new) ?PP | W ?PP | W ?PP | W (was C) 2PP
| As a user, I want to be able t osee the (same) events when I have shut down the application and have started it again (in case of no network connection) | As a citizen I want to find out about an escape route that is close or sutiable for my location | As a helper I would like to find out how to help in a specific incident (assuming events have been categorized and matched to my abilities) | As a user I rate the helper after the event
Finished during iteration one
| M 2PP | M 4PP | M 6PP | C (new) 1PP
| As a helper I specify where and for which Event I am going to help | As a citizen I want to see what is happening where in a specified area. Selection of event provides extra information (assumption list of events exists including location) | As a user I want to create an account and to set up a profile providing information about my gender, age, first aid certifications etc. | As an user I want to delete an event
| Task: Account system 4PP |  | Tasks: Account system 4PP
| Task: Account system 4PP |  | Task: GUI 2PP
S 4PP
As a system manager I want to update/delete accounts
Task: Create account system 4PP
Task: Create GUI 4PP
Finished during iteration one
| M 4PP | S 2PP | S (new) 2PP | S (new) 1PP
| As a citizen I want to report an incident or event with a location and a description | As a government agency I report an event that the general public should be aware of | As an user I want to log in to the system | As an user I want to be able to log off
Task: createing the list 2PP
Task: entering an event 2PP

## Iteration two
Must
| M 2PP | M 4PP | M 6PP
| As a helper I specify where and for which Event I am going to help | As a citizen I want to see what is happening where in a specified area. Selection of event provides extra information (assumption list of events exists including location) | As a user I want to create an account and to set up a profile providing information about my gender, age, first aid certifications etc.
| Task: Account system 4PP |  | Tasks: Account system 4PP
| Task: Account system 4PP |  | Task: GUI 2PP
Should
| S 1PP | S 8PP | S 6PP
| As an user, I want to be able to tell that an event is over | As a system manager I want to update/delete accounts | As a helper I only want to see events where I can help (assumption: list of events exists, including locations)
|  | Task: Create account system 4PP | Task: categorizing of events 4PP
|  | Task: Create GUI 4PP | Task: showing selection 4PP
| New S 2PP | New S 4PP | S 1PP
| As an user, I want to delete my account | As an user, I want to add information to an event | As an user I want to see the alerts on the top of the list
Could
| C 2PP | C 2PP | C 3PP
| As a user I want to vote for the urgency of an event and validate this property | As a user I rate the helper after the event | As a journalist I want to provide information that helps to validate the severity of a given event
Would
| W ?PP | W ?PP | W ?PP | W 2PP
| As an user I want to report an event via Twitter (assuming eventlist exists) | As a citizen I want to find out about an escape route that is close or sutiable for my location | As a helper I would like to find out how to help in a specific incident (assuming events have been categorized and matched to my abilities) | As an observer I would like to see where every incident is located in the interactive map
Finished during iteration one
| M 4PP | S 2PP | S (new) 2PP | S (new) 1PP
| As a citizen I want to report an incident or event with a location and a description | As a government agency I report an event that the general public should be aware of | As an user I want to log in to the system | As an user I want to be able to log off
Task: createing the list 2PP
Task: entering an event 2PP

## Iteration one
Must
| M 2PP | M 4PP | M 4PP
| As a helper I specify where and for which Event I am going to help | As a citizen I want to see what is happening where in a specified area. Selection of event provides extra information (assumption list of events exists including location) | As a citizen I want to report an incident or event with a location and a description
| Task: Account system 4PP |  | Task: createing the list 2PP
| Task: Account system 4PP |  | Task: entering an event 2PP
Should
| S 1PP | S 8PP | S 6PP | S 2PP
| As a user I want to create an account and to set up a profile providing information about my gender, age, first aid certifications etc. | As a system manager I want to update/delete accounts | As a helper I only want to see events where I can help (assumption: list of events exists, including locations) | As a user I want to vote for the urgency of an event and validate this property
Task: categorizing of events 4PP
Task: showing selection 4PP
| S 2PP | S 2PP | S 1PP | S 1PP
| As a government agency I report an event that the general public should be aware of | As an user I want to log in to the system | As an user I want to be able to log off | As an user I want to see the alerts on the top of the list
Could
| C 1PP | C 2PP | C 3PP | C 2PP
| As an user, I want to be able to tell that an event is over | As a user I rate the helper after the event | As a journalist I want to provide information that helps to validate the severity of a given event | As an observer I would like to see where every incident is located in the interactive map
Would
| W ?PP | W ?PP | W ?PP
| As an user I want to report an event via Twitter (assuming eventlist exists) | As a citizen I want to find out about an escape route that is close or sutiable for my location | As a helper I would like to find out how to help in a specific incident (assuming events have been categorized and matched to my abilities)